## Team Structure
Role | Responsibilities | Required Skills | Experience Level
Frontend Developer | UI/UX implementation, React development, responsive design | JavaScript, React, CSS, HTML | Junior to Senior
Backend Developer | API development, database design, server architecture | Node.js, Python, SQL, REST APIs | Mid to Senior
Full Stack Developer | End-to-end feature development, system integration | JavaScript, Python, databases, cloud | Senior
DevOps Engineer | CI/CD pipelines, infrastructure management, monitoring | Docker, Kubernetes, AWS, Jenkins | Senior
Tech Lead | Architecture decisions, code reviews, mentoring | Multiple languages, design patterns, leadership | Senior+
Product Manager | Requirements gathering, feature prioritization, stakeholder communication | Business analysis, agile methodologies | Mid to Senior
QA Engineer | Test planning, automation, quality assurance | Testing frameworks, automation tools | Junior to Senior
Data Engineer | Data pipelines, analytics, data modeling | Python, SQL, ETL tools, big data | Mid to Senior

## Project Timeline
Phase | Tasks | Duration (weeks) | Dependencies | Deliverables
Planning | Requirements analysis, technical design, resource allocation | 2 | Stakeholder approval | Project plan, technical specs
Setup | Environment setup, repository creation, CI/CD pipeline | 1 | Planning complete | Development environment
Development Sprint 1 | Core API development, basic frontend | 3 | Setup complete | MVP backend, basic UI
Development Sprint 2 | Feature implementation, database integration | 3 | Sprint 1 complete | Feature-complete backend
Development Sprint 3 | Frontend completion, UI/UX polish | 3 | Sprint 2 complete | Complete frontend
Testing | Integration testing, performance testing, security audit | 2 | Development complete | Test reports, fixes
Deployment | Production deployment, monitoring setup | 1 | Testing complete | Live application
Monitoring | Performance monitoring, bug fixes, optimization | Ongoing | Deployment complete | Stable production system

## Technology Stack
Category | Technology | Version | Purpose | Alternatives
Frontend Framework | React | 18.x | User interface development | Vue.js, Angular, Svelte
Backend Framework | Node.js with Express | 18.x | Server-side API development | Python Django, Java Spring
Database | PostgreSQL | 15.x | Primary data storage | MySQL, MongoDB, SQLite
Cache | Redis | 7.x | Session storage and caching | Memcached, Amazon ElastiCache
Container Platform | Docker | 24.x | Application containerization | Podman, containerd
Orchestration | Kubernetes | 1.28.x | Container orchestration | Docker Swarm, Amazon ECS
CI/CD | GitHub Actions | Latest | Continuous integration and deployment | Jenkins, GitLab CI, CircleCI
Monitoring | Prometheus + Grafana | Latest | Application and infrastructure monitoring | DataDog, New Relic
Cloud Provider | AWS | Latest | Infrastructure hosting | Google Cloud, Azure, DigitalOcean
Authentication | Auth0 | Latest | User authentication and authorization | Firebase Auth, AWS Cognito

## Best Practices
Category | Practice | Priority | Implementation Status | Notes
Code Quality | Use consistent code formatting (Prettier, ESLint) | High | Implemented | Automated in CI pipeline
Code Quality | Write comprehensive unit tests (>80% coverage) | High | In Progress | Currently at 65% coverage
Code Quality | Conduct regular code reviews | High | Implemented | All PRs require 2 approvals
Security | Implement input validation and sanitization | Critical | Implemented | Using Joi for validation
Security | Use HTTPS for all communications | Critical | Implemented | SSL certificates auto-renewed
Security | Regular dependency updates and security scans | High | Implemented | Automated with Dependabot
Performance | Implement caching strategies | Medium | Implemented | Redis caching for API responses
Performance | Optimize database queries | Medium | In Progress | Adding indexes and query optimization
Deployment | Use blue-green deployment strategy | Medium | Planned | Will implement in Q3
Monitoring | Set up comprehensive logging | High | Implemented | Using structured logging with Winston
Documentation | Maintain API documentation | Medium | Implemented | Auto-generated with Swagger
Documentation | Keep README and setup guides updated | Medium | Implemented | Updated weekly during sprints